## Planning
AudaciaBall
Planning
N° | Category | What to do | Done? | Time it took (hours)
1 | Setup | Excel planning | Yes | 0.5
2 | Setup | Create Git repo | Yes | 0.1
3 | Setup | Install node.js (vue) | Yes | 0.1
4 | Setup | Create project + empty DB (Visual Studio) | Yes | 0.1
5 | Design | Create UI mockups | Yes | 0.5
6 | Design | Model DB | Yes | 0.5
7 | Dev | Create UI routes with Vue.JS in Visual Studio | Yes | 1
7.1 | Dev | Add UI components | Yes | 2
8 | Dev | Create DB SQL Server | Yes | 0.5
9 | Dev | Create API in C# with Visual Studio | Yes | 4.5
10 | Test | Test API | Yes | 1
10.1 | Deploy | Create DB on Azure | Yes | 0.5
10.2 | Deploy | Deploy API on Azure | Yes | 2
11 | Dev | Integrate API with Vue.JS UI
12 | Test | Test UI
13 | Deploy | Deploy UI on web
14 | Documentation | Document front and backend
15 | Documentation | Document user guide for installation
13.3

## Used
vue-router | installed with npm
vue-cli | installed with npm
Cors | installed with install-package

## ToDo API
What | Parameters | Done?
AddTeam | string name, int player1, int player2 | Yes
AddPlayer | string name | Yes
AddGame | int player1, int player2, int scoreBlue, int scoreRed, date date | Yes
GetGameHistory | int idPlayer | Yes
GetAllGames |  | Yes
GetAllPlayers |  | Yes
GetAllTeams |  | Yes