## Feuil1
AudaciaBall
Planning
N° | Category | What to do | Done? | Time it took (hours)
1 | Setup | Excel planning | Yes | 0.5
2 | Setup | Create Git repo | Yes | 0.1
3 | Setup | Install node.js (vue) | Yes | 0.1
4 | Setup | Install PostgreSQL
5 | Design | Create UI mockups
6 | Design | Model DB
7 | Dev | Create UI with Vue.JS in Visual Studio
8 | Dev | Create DB with PostgreSQL
9 | Dev | Create API in C# with Visual Studio
10 | Test | Test API
11 | Dev | Integrate API with Vue.JS UI
12 | Test | Test UI
13 | Deploy | Simply deploiement with Docker
14 | Documentation | Document front and backend
15 | Documentation | Document user guide for installation